## Sheet1
Category | MVP definition | 2020-10-17 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18
bot sys | bot_mvp1 (flow#3,4,5,6,7,13,16,17-change) | 2020-10-23: bot_mvp1 internal testing (for R&D); 2020-11-06: bot_mvp1 accept testing (for Jane and Angelina)
| bot_mvp2 (flow#1,2,17-cancel) | 2020-10-30: bot_mvp2 internal testing (for R&D); 2020-11-13: bot_mvp2 accept testing (for Jane and Angelina)
| bot_mvp3 (flow#8,9,10,11,12,14) | 2020-11-13: bot_mvp3 internal testing (for R&D); 2020-11-27: bot_mvp3 accept testing (for Jane and Angelina)
training sys | train_mvp1: Automatic discovery of problems | 2020-11-06: train_mvp1 internal testing (for R&D)
| train_mvp2: update knowledge bank | 2020-11-13: train_mvp2 internal testing (for R&D)
| train_mvp3: Automatic test and verification of bot | 2020-11-20: train_mvp3 internal testing (for R&D); 2020-12-04: training sys accept testing
app client | app_design | 2020-10-17: app_design review done
| app_mvp1: send alerts and display the request | 2020-11-06: app_mvp1 internal testing (for R&D)
| app_mvp2: staff action and update the request | 2020-11-20: app_mvp2 internal testing (for R&D); 2020-12-04: app client accept testing (for Jane and Angelina)
pc web | pc_design | 2020-10-23: pc_design review done
pc_mvp1: (pending for requirement and design ready)
what should be prepared |  | 2020-10-17: app_design document (Johnson); 2020-10-23: pc_design document (Dasiy); 2020-10-30: bot_mvp2 internal testing enviroment (johnson); 2020-11-13: bot_mvp3 internal testing enviroment (johnson)
|  |  | bot_mvp1 testing enviroment (Johnson) | knowledge bank for bot_mvp3 (angelina) | bot_mvp1 accept testing enviroment and internal testing report (johnson) | bot_mvp2 accept testing enviroment and internal testing report (johnson) |  | bot_mvp3 accept testing enviroment and internal testing report (johnson)
|  | knowledge bank for bot_mvp1 (angelina) | knowledge bank for bot_mvp2 (angelina) | bot_mvp1 accept testing cases (Jane and Angelina) | bot_mvp2 accept testing cases (Jane and Angelina) | app_mvp1 internal testing enviroment (johnson) | bot_mvp3 accept testing cases (Jane and Angelina) | app client accept testing cases (Jane and Angelina)
|  |  |  | amazon account for accept testing (Jane) | app_mvp1 internal testing enviroment (johnson) |  | app_mvp2 internal testing enviroment (johnson)
train internal testing enviroment (johnson)